## Project Plan
Phase 1 - Data Foundation | Status
Week 1 - ERCOT Data Acquisition and Loaders
Setup
◯Create GitHub repo, Python virtual environment, project folder structure (data/, loaders/, models/, api/, frontend/) | Done
◯Install core libs: requests, pandas, sqlalchemy, pydantic, pytest | In Progress
ERCOT historical download
◯Download YTD of Day-Ahead (DA) LMP prices from ERCOT API or bulk CSV — understand settlement point structure, hub vs node pricing | Done
◯Download Real-Time (RT) 15-min interval prices — understand how RT diverges from DA and why that creates optimization opportunity | Done
◯Download Ancillary service prices: RegUp, RegDown, ECRS, Non-Spinning Reserve — understand AS capacity vs energy market difference | In Progress
◯Download renewable generation data (solar + wind) and load data (system-wide demand) — these become features for price forecasting later | In Progress
◯Download load data | In Progress
Loaders
◯Write a historical loader class per data type — reads raw CSVs, normalizes column names, parses timestamps to UTC, returns clean DataFrames | Do After DB Design
◯Write unit tests for each loader — test that shape, types, and timestamp parsing are correct on sample files
Week 2 - Database Schema, Pre-Processing and Daily Loaders
Database design
◯Design schema: da_prices (interval_start, settlement_point, price), rt_prices (interval_start, settlement_point, price), ancillary_prices (interval_start, service_type, price), renewable_gen, load_data, battery_config, optimization_results | Done
◯Set up SQLite for local dev with SQLAlchemy ORM — schema designed so you can swap to PostgreSQL on Railway/Render later with zero code changes | Done
◯Design battery_config table: capacity_kwh, max_charge_kw, max_discharge_kw, round_trip_efficiency, min_soc_pct, max_soc_pct, degradation_cost_per_kwh — these become LP constraints | Done
Preprocessing pipeline
◯Handle missing intervals — ERCOT data has gaps; decide on forward-fill vs interpolation strategy, document the choice | In Progress
◯Align all data to a common 15-min interval index — RT is 15-min, DA is hourly, resample DA to 15-min for consistency | In Progress
◯Seed database with all historical data — write a one-time bulk insert script using SQLAlchemy batch operations (not row-by-row) | Done
Daily incremental loader
◯Write a DailyLoader that hits ERCOT API each morning, fetches yesterday's actuals + today's DA prices, upserts into DB (no duplicates) | In Progress
◯Schedule with APScheduler or a simple cron job — runs at 7am after ERCOT publishes DA results | In Progress
Phase 2 - Optimization Engine
Week 3 - LP Optimization - Energy Arbitrage
Learn LP formulation (days 1–2)
◯Read PuLP documentation and do 2 simple examples — understand decision variables, objective function, constraint syntax
◯Sketch your problem on paper: decision variables = charge_t and discharge_t for each 15-min interval t; objective = maximize revenue from discharging minus cost of charging
Build the LP model (days 3–5)
◯Implement BatteryLP class: loads battery_config from DB, accepts a price series (96 intervals for 24h), returns optimal charge/discharge schedule
◯Add all physical constraints: SOC continuity (SOC[t] = SOC[t-1] + η·charge[t] − discharge[t]), SOC bounds [min_soc, max_soc], charge/discharge rate limits, mutual exclusivity (can't charge and discharge simultaneously — use binary variable here or big-M)
◯Test on 1 day of historical DA prices — plot the schedule, verify it actually charges at low-price hours and discharges at high-price hours
◯Run backtest on 30 days of history — compute total $ revenue, compare to naive strategy (charge off-peak, discharge on-peak)
Week 4 - Add Ancillary Services & 7 - Day Horizon
Ancillary service co-optimization
◯Extend LP to include AS capacity awards — add decision variables for reg_up_t and reg_down_t (MW reserved for regulation)
◯Add AS feasibility constraints: reserved headroom for reg_up reduces available discharge capacity; reserved footroom for reg_down reduces available charge capacity
◯Add AS revenue to objective: each MW of regulation capacity earns the AS price per interval — the model now trades off energy arbitrage vs AS revenue
◯Test: verify that high AS prices cause model to hold more capacity in reserve rather than charge/discharge aggressively
7-day rolling horizon
◯Extend model to 672 intervals (7 days × 96 intervals/day) — confirm solver still runs in under 60 seconds
◯For days 2–7, use DA price forecasts — start simple: use historical same-day-of-week average prices as the forecast input. Note this as a future improvement.
◯Write results to optimization_results table: run_timestamp, horizon (next_day / next_7_day), interval_start, charge_kw, discharge_kw, soc_pct, energy_revenue, as_revenue
Week 5 - Real-time re-optimization trigger
RT price monitor
◯Write an RTMonitor that polls ERCOT RT price endpoint every 5 minutes and compares to the DA price used in the current schedule
◯Define re-trigger threshold: if ¦RT_price − DA_price¦ > $X/MWh for 2+ consecutive intervals, flag a re-optimization event
◯Store RT deviations in a rt_deviation_log table — useful for showing on the dashboard later
Warm-start re-optimization
◯When triggered, re-run LP from current interval to end of day using actual RT prices for past intervals and updated RT forecast for remaining intervals
◯Fix current SOC as initial condition — the battery is at whatever state it's at right now, not the original start-of-day assumption
◯Store re-optimized schedule alongside original schedule so you can show the delta on the dashboard ("revised vs original")
Backtesting
◯Run 90-day backtest: DA-only optimization vs DA + RT re-optimization — compute $ improvement from re-optimization. This becomes a key resume stat.
Phase 3 - Backend API
Week 6 - FastAPI backend & REST End points
API structure
◯Set up FastAPI app with SQLAlchemy session dependency injection, Pydantic response models, and auto-generated OpenAPI docs
◯GET /schedule/today — returns optimized 24h charge/discharge schedule for today with prices
◯GET /schedule/7day — returns 7-day rolling schedule
◯GET /prices/da and GET /prices/rt — returns price time series for charting
◯GET /battery — returns current battery config; PUT /battery — updates config and triggers re-optimization
◯GET /analytics/revenue — historical revenue breakdown: energy arbitrage vs AS, realized vs scheduled
◯GET /alerts/rt-deviations — returns recent RT price spikes and re-optimization events
Background tasks
◯Add APScheduler to FastAPI app: daily loader at 7am, RT monitor polling every 5 min, 7-day re-optimization every Sunday evening
◯Write integration tests for every endpoint using httpx + a test SQLite database
Phase 4 - Frontend Dashboard
Week 7 - REACT Dashboard - Schedule & Price Charts
Setup
◯Scaffold with Vite + React + TypeScript. Add Recharts for data visualization, TanStack Query for API data fetching, Tailwind CSS for layout
Core views
◯Today's schedule chart: dual-axis time series — bar chart of charge/discharge kW (positive = charge, negative = discharge) overlaid with DA and RT price line. The most important visual in the whole app.
◯SOC timeline: area chart showing state of charge % across the day, annotated with min/max bounds from battery config
◯7-day view: scrollable timeline of the rolling 7-day schedule with daily revenue totals
◯Revenue summary cards: today's energy revenue, AS revenue, cumulative 30-day revenue, vs-baseline improvement from RT re-optimization
Week 8 - Battery Config UI, RT Alerts & Analytics
Battery parameter panel
◯Form with sliders + number inputs: capacity (kWh), max charge/discharge rate (kW), round-trip efficiency (%), min/max SOC (%), degradation cost ($/kWh)
◯On save: PUT /battery → triggers re-optimization → dashboard auto-refreshes with new schedule. User sees impact of their config change immediately.
RT alerts feed
◯Live alert panel showing recent RT deviation events: timestamp, magnitude of price spike, whether re-optimization was triggered, revenue delta
◯Use WebSocket or polling to update in near-real-time
Analytics tab
◯Historical revenue chart (30/90 day), revenue split by energy vs AS, DA schedule vs RT actuals comparison, re-optimization event log with $ impact
Phase 5 - Polish & Portfolio
Week 9 - Postgress SQL migration, test & deployment
Production hardening
◯Migrate from SQLite to PostgreSQL on Railway (free tier) — change SQLAlchemy connection string, run Alembic migration, verify all queries work
◯Add proper database indexes: on interval_start for all time-series tables, on settlement_point for price tables — query the execution plan, show it speeds up by 10x+
◯Add environment-based config with python-dotenv — no hardcoded secrets anywhere
◯Write a GitHub Actions CI pipeline: runs tests on every push, fails if coverage drops below 70%
Error handling & observability
◯Add structured logging to all loaders and optimization runs — log solver status, solve time, revenue computed
◯Add a GET /health endpoint that checks DB connectivity and last successful data load time
Week 10 - Readme, Write-up & Resume Bullets
Documentation
◯Write a detailed README: problem statement, architecture diagram, LP formulation explained in plain English, tech stack, setup instructions, screenshots
◯Write a technical write-up (500–800 words) explaining the optimization approach, constraint design decisions, and what you learned — post on GitHub or a simple blog
Resume & interview prep
◯Craft 2–3 resume bullets that lead with CS primitives: "Built an LP-based battery dispatch optimizer over 96 15-min intervals using PuLP; added real-time re-optimization trigger on ERCOT price deviations exceeding $X/MWh"
◯Prep answers to: "Walk me through your LP formulation", "How did you handle the mutual exclusivity constraint?", "How would you scale this to 100 batteries?"
◯Record a 2-min screen demo video — link it in your LinkedIn and resume. Recruiters love a live demo they can watch in 2 minutes.